# FieldMesh Backend Work Split: Athidh and Rogith

React Native MVP, 17 hours backend time

# Overview

The backend work is split equally between Athidh and Rogith, 17 hours each.

- Athidh: everything local. Hotspot, local TCP hub, site session join, photo transfer on site and the Nearby chain relay.

- Rogith: everything cloud and shared. Server, database, merge engine, on-device storage, photo uploads and deployment.

MVP tasks come first for both. Stretch tasks come last, so they can be cut without breaking the demo.

# Hour 0 to 1: Together

- Agree on the shared edit format (id, fieldId, value, author, device, hlc, parents, schemaVersion).

- Agree on one transport interface: send(bytes), onReceive(bytes), onStatus(). Both people’s code plugs into this, so neither blocks the other.

- Add every native library on day one and make one dev build, so later rebuilds are rare.

# Athidh: Hotspot, Local Hub and Chain Relay (17 hours)

| Hours | Task | Type |
| --- | --- | --- |
| 1 to 2.5 | Transport layer: message framing, Yjs state vector sync over any byte channel | MVP |
| 2.5 to 4.5 | Kotlin module for local-only hotspot, permissions, dev build | MVP |
| 4.5 to 7 | TCP hub (react-native-tcp-socket): session key check, sync, broadcast to all spokes | MVP |
| 7 to 8 | Site session: Wi-Fi QR and session QR, join flow | MVP |
| 8 to 9.5 | Heartbeat, auto reconnect, keep-awake, foreground service for the hub | MVP |
| 9.5 to 11.5 | Photo chunks over TCP with resume | MVP |
| 11.5 to 14.5 | Nearby Connections Kotlin module, chain relay forwarding | MVP |
| 14.5 to 16 | QR-frame fallback transport | Stretch |
| 16 to 18 | Real device testing: hotspot, bridge phone, Bluetooth fallback | MVP |

# Rogith: Cloud Backend, Merge Engine and Storage (17 hours)

| Hours | Task | Type |
| --- | --- | --- |
| 1 to 3 | Server setup: Fastify, Hocuspocus, SQLite, Docker | MVP |
| 3 to 5 | Auth (JWT), teams, inspections API | MVP |
| 5 to 8 | Edit log: HLC, parents, per-field rules, dispute detection (shared code) | MVP |
| 8 to 9.5 | On-device SQLite: Yjs updates, photo queue | MVP |
| 9.5 to 11 | Server persistence hooks: updates, snapshots, edits table | MVP |
| 11 to 13.5 | Photo hashing on phone, tus upload queue, server hash verify, MinIO | MVP |
| 13.5 to 15 | History, disputes and resolve APIs | MVP |
| 15 to 16.5 | Cloud deploy (Render or Railway), merge correctness test script | MVP |
| 16.5 to 18 | Schema lens v1 to v2 | Stretch |

# Why the Weight Is Equal

Both lists total 17 hours. Athidh has fewer tasks, but they are heavier native work (Kotlin modules, device testing). Rogith has more tasks, all in JavaScript and TypeScript, which iterate faster.

# Checkpoints

| Hour | Athidh | Rogith |
| --- | --- | --- |
| 5 | Hotspot starts from the app | Server syncs a document over the cloud |
| 9 | Three phones sync live through the hub | Disputes show up from the edit log |
| 14 | Chain relay reaches a phone outside hotspot range | Photos upload with resume and hash verification |
| 16 | Device testing, bug fixes, rehearsal | Device testing, bug fixes, rehearsal |

The MVP is locked at hour 14. Everything after that is testing or stretch.

# Build Notes

- Only Athidh’s Kotlin changes need a rebuild. Rogith’s work is JavaScript and updates instantly with Fast Refresh.

- Keep test phones on USB and run adb reverse tcp:8081 tcp:8081, so they stay connected to Metro after joining the hotspot.

- Hotspot and Nearby Connections are Android only, so use Android phones for the demo.

# If Time Runs Short

- Athidh: cut the QR-frame fallback first, since your own hotspot hub is reliable.

- Rogith: cut the schema lens.

The chain relay and every hard part of the brief (sync protocol, schema handling, resumable media) stay in.

# Not Covered Here

Frontend and UI are outside this split. Whoever owns the screens should plug into the transport interface and the edit log APIs from hour 1.